## Sheet1
Project | Area | Priority | Status | Responsible | Deadline | What needs to be done? (Task) | Links & Storage Location | Comments / Info | Authorities | Restrictions | Feedback
P I: procoli, Marketing | Website Relaunch procoli.io | 🔥 Immediate | In Review | andreas | 2025-12-27 | Send design approval to agency | [Link to Figma/Drive] | Agency is urgently waiting! | adaptations in CI | Color codes, fonts
P II: wevalco, Accounting | Year-end Closing | 👉 Important | In Progress | michael | 2026-01-02 | Upload December invoices | [Link to Datev/Folder] | Please pay attention to cost center 402
Marketing | Social Media Comments | 🧊 Can wait | Open | Mona | - | Answer LinkedIn comments | https://www.linkedin.com/company/procoli/ | Only do if everything else is completed | respond on behalf of procoli | Private messages
P I: procoli, Marketing | Organic Content | 👉 Important | Done | Mona | 2025-11-26 | December Social Media pre-planning | Link to calendar overview | Christmas Advent content, logo with Santa hat |  | Performance Ads | smooth operation